## Slide 1: 3rd HAWEN Executive Committee meeting, 3-5 march 2020
Report on hawen activities since the last hawen executive committee meeting

## Slide 2: Key recommendations of the last hawen executive committee & Actions taken (1)
HAWEN members that have not yet completed ICCWC country assessments should work with the IGAD Secretariat to request support for assessments from ICCWC; and the Executive Committee welcomes the offer of support from ICCWC and requests IGAD to follow up.
  At the request of Djibouti, IGAD wrote an official letter to ICCWC which responded positively.
Continue work towards realization of an IGAD/AU Five Year Action Plan to Combat Wildlife Crime in the Horn of Africa;
  IGAD and AU developed the Five Year Action Plan; AU to expedite the finalization of the joint workplan and cooperation agreement.
Agree that the IGAD Secretariat should work with HAWEN member countries and the AU to develop a joint proposal for submission to potential funding sources for operationalization of the HAWEN Secretariat and implementation of the HAWEN Action Plan;
  Worked together with member states and AU and presented HAWEN Action Plan at COP18 to mobilize resources for HAWEN
  IGAD submitted a proposal to EU Brussels through the IGAD Committee of Ambassadors in Brussels

## Slide 3: Key recommendations of the last hawen executive committee & Actions taken (2)
IGAD in collaboration with its member states should work with HAWEN Partners to explore the potential of a regional TWIX platform for data / information and experience sharing;
  IGAD was discussing with TRAFFIC and REO of the US Embassy in Addis for such a platform
  The matter can be discussed during the TWIX workshop on 4 March 2020
Decide to begin the process of negotiating a HAWEN regional protocol concerning wild animals confiscated from cross-border wildlife trafficking;
  IGAD was waiting for comments from member states to finalize the draft protocol; MSs to provide their comments
Endorse a Joint Statement of the African Union and IGAD concerning cooperation to combat wildlife crime in the Horn of Africa region;
  Will be undertaken as part of the Cooperation Agreement between IGAD and AU for the implementation of the Five Year Action Plan

## Slide 4: Key recommendations of the last hawen executive committee & Actions taken (3)
Decide that the HAWEN should be represented at the Third Global Meeting of WENs by the Chair of the HAWEN Executive Committee and a representative of IGAD and, if possible, to organize a HAWEN side event to increase awareness and resource mobilization.
  Chair of HAWEN and IGAD representative participated at the WEN meeting
  With the support of REO of the US, Embassy in Addis all the documents of HAWEN in a thumb drive with a covering letter were distributed to potential Partners
  Contacts with different WENs was initiated
Develop and operationalize the HAWEN website/training materials library.
  Websites under development with the financial support of the Netherlands
  Mr. Busuri will present and introduce us to the HAWEN Web-site
Enhance cooperation between the HAWEN and the LATF on regional wildlife law enforcement;
  HAWEN participated at the LATF meeting in May 2019
  LATF Action Plan developed with activities to be implemented with the involvement of different stakeholders, including IGAD

## Slide 5: Key recommendations of the last hawen executive committee & Actions taken (4)
Strengthen relationships between the HAWEN and other regional WENs.
  Some relationship between HAWEN and other WENs initiated during COP18
Finalize and distribute the report (list of participants, agenda, presentations) of the workshop latest by end of March 2019;
  Report finalized on time and distributed to participants
IGAD to write an official letter to member states requesting them to designate the HAWEN focal person;
  IGAD wrote an official letter to member states
Other Activities
  HAWEN Chair and the IGAD Representative attended UNODC meeting on 25-27 February 2020
  The Chair presented HAWEN while the IGAD representative present the IGAD Wildlife Management Strategy
  We have good discussions with UNODC, Mike and CMS experts on how we can cooperate and the support HAWEN can get from their projects
  I am happy that Mr. Javier is among us and will brief the EC on the kind of support and collaboration HAWEN will enjoy from the EU Cross-regional Wildlife Program for EAC, IGAD, SADC and IOC being implemented by UNODC and others.

## Slide 6: Key challenges faced
Funding.
  To operationalize the HAWEN Secretariat
  To implement HAWEN Action Plan
Delay in signing of HAWEN Protocol by Kenya
  There was discussion that the former ES of IGAD would meet the Kenyan Minister, but did not happen
  The Minister was also planning to travel to Djibouti to sign the Protocol, but with the departure of the previous IGAD ES, this was delayed again
  We are working that the new ES travels and meets the Kenyan Minister
Delay of AU and IGAD Cooperation
  Joint Action Plan developed
  However, signing of the cooperation agreement not undertaken
  AU requested to expedite

## Slide 7: opportunities
There are national and regional projects that HAWEN can tap into
  Cheetah project supported by DFID
  Ethiopian (EWCA) project implemented by UNDP
  Counter wildlife trafficking in the aviation sector, AWF
Other Programmes
  EU Cross-regional Wildlife Programme
  Other EU and GEF initiatives
  Tap again into CITES activities
Member States support
  Budget for running of the Secretariat
  Find out if member states can support through staff secondment
  Budget for the implementation of the HAWEN Action Plan
Second Phase of BMP
  Second phase approved (Boma-Gambela Park, 4.5 m Euros)
  EUD in Juba will be responsible
  There will be some funds for IGAD’s coordination activities
  There will be also some funds for database and capacity building

## Slide 8
THANK YOU FOR YOUR ATTENTION